## FL Poly
State University System of Florida Board of Governors
University Support Organizations Internal Control Review
FL Poly Crowe Report Findings Corrective Action Status, May 2023
Please confirm or update the corrective actions status, the estimated completion date (if applicable), and the additional comments cell(s).
DSO | Area | Control Deficiency | Finding | Corrective Actions Status | If Not Completed, Estimated Completion Date | Additional Comments
FL Poly Foundation | Journal Entries | Segregation of Duties | Journal entries and reconciliation reviews were prepared and posted by the same individual. | Pending | 2023-06-30 | December 2022 Update: DSO is in the process of hiring additional staff. Once staffed and appropriate controls are established, University Audit will perform follow up to ensure corrective action has been taken. February 2023 Update: The DSO hired an accountant that started on 2/6/23. As noted above, once appropriate controls have been established and placed into operation for a sufficient amount of time, University Audit will perform follow-up. May 2023 Update:
FL Poly Foundation | Accounts Receivable | Segregation of Duties | Journal entries and reconciliation reviews were prepared and posted by the same individual. | Pending | 2023-06-30 | December 2022 Update: See above. February 2023 Update: May 2023 Update:
FL Poly Foundation | Cash Management | Segregation of Duties | Journal entries and reconciliation reviews were prepared and posted by the same individual. | Pending | 2023-06-30 | December 2022 Update: See above. February 2023 Update: May 2023 Update:
FL Poly Foundation | Investment Management | Segregation of Duties | Journal entries and reconciliation reviews were prepared and posted by the same individual. | Pending | 2023-06-30 | December 2022 Update: See above. February 2023 Update: May 2023 Update:

## NCF
State University System of Florida Board of Governors
University Support Organizations Internal Control Review
NCF Crowe Report Findings Corrective Action Status, May 2023
Please confirm or update the corrective actions status, the estimated completion date (if applicable), and the additional comments cell(s).
DSO | Area | Control Deficiency | Finding | Corrective Actions Status | If Not Completed, Estimated Completion Date | Additional Comments
New College Foundation, Inc. | Corporate Governance | Supporting Documentation | Review of budget-to-actual variances were not documented. | Pending | 2023-03-31 | December 2022 Update: Waiting for next quarterly budget variance report to test corrective actions. February 2023 Update: Budget-to-actual variance presentation created. Pending presentation to the Foundation Board of Director's Finance Committee and university's Board of Trustees in March 2023. May 2023 Update: The Foundation fully agrees that a quarterly review of the budget to actual results on a timely basis is an excellent best practice, and has taken steps to implement this recommendation. The Foundation has worked closely to develop a budget to actual variance analysis that will help the Board of Directors understand where actual expenses vary from the approved budget. The second quarter variance analysis was discussed with the Foundation Board of Directors at the meeting of January 27. The unexpected resignation of the long-time Foundation Executive Director in January, several Foundation Board members, and both fiscal staff in April, has created a disruption in operations, and delayed production of the third quarter budget to actual variance analysis. We have every confidence that the Foundation will get back on track with the close of the 4th quarter, and plan to present and discuss the budget to actual variance report at the August 11, 2023 meeting of the Foundation Board.

## UCF
State University System of Florida Board of Governors
University Support Organizations Internal Control Review
UCF Crowe Report Findings Corrective Action Status, May 2023
Please confirm or update the corrective actions status, the estimated completion date (if applicable), and the additional comments cell(s).
DSO | Area | Control Deficiency | Finding | Corrective Actions Status | If Not Completed, Estimated Completion Date | Additional Comments
UCF Athletics Association, Inc. | Accounts Receivable | Review and Approval | Management did not document the preparation or review for account reconciliations. | Pending | 2023-05-31 | December 2022 Update: Corrective action will be taken to ensure accounts receivable is reconciled from the bank statements/invoices/and ledger reports in Workday. Documentation of the review and approval of these reconciliations will be recorded by the Assistant Controller and Controller as appropriate. February 2023 Update: The search to replace the Assistant Controller for DSO Operations who will have responsibility for this activity remains in progress. May 2023 Update:
UCF Athletics Association, Inc. | Cash Management | Review and Approval | Management did not document the preparation or review for account reconciliations. | Pending | 2023-05-31 | December 2022 Update: Corrective action will be taken to ensure cash management reconciling of the manual bank statement review to the Workday ad hoc bank transactions and settlement runs. Documentation of the review and approval will be recorded by the Assistant Controller and Controller as appropriate. The position that previously reviewed ad hoc bank transactions and submitted to management for approval is vacant. The Controller for DSO Operations has launched a search to replace this position and expects to have someone hired by 2/1/2023. February 2023 Update: The search to replace the Assistant Controller for DSO Operations who will have responsibility for this activity remains in progress. May 2023 Update:
UCF Foundation, Inc. | Investment Management | Completeness/Timeliness/Accuracy | Investment account reconciliations were not performed timely. | Pending | 2023-05-31 | December 2022 Update: This issue was related to the COVID crisis and delays in getting this review completed. Completion date has been estimated to accommodate ongoing challenges related to the Workday implementation. February 2023 Update: Completion date has been estimated to accommodate ongoing challenges related to the Workday implementation. May 2023 Update:

## Dropdowns (hidden)
Corrective Actions Status
Completed
Not Started
Pending