## Sheet1
2026-27 Fiscal Year Internal Audit, Risk Management, and Compliance Activity Plan Final
Project Description | Company Contact | Auditor | Hours To Complete | Location | Audit Budget Impact | Planned Audit Period | Objective/Status | Risk Management Impact
Internal Audits
Support State Auditor General and BOG Inspector General Audits | All Department Managers | Audit Exec | 160 | Campus wide | 0 | Ongoing all Year | Support seamless completion of State Auditor General Financial Statement, Operational, and Financial Aid audits as well as BOG Inspector General audit requests. | Ensure good standing with State Auditor General's office and Board of Governors' Inspector General with timely and complete request responses and reliable identified deficiency remediation.
IT General Control and Cyber Security Penetration and Social Engineering Tests | Chief Information Security Officer (CISO) | Audit Exec | 80 | Campus wide IT Resources | 20000 | December | Confirm the design and effectiveness of IT general controls and cyber security measures, including an external penetration and phishing vulnerability tests to enhance access security. | Reduce risk of cyber breach and data ransom including interruption in access to, corruption of, or loss of university data processing systems and/or critical information. Avoid reputation damage.
Audit University Departments' Level of Security Over Protected Data Including Periodic Application Access Reviews | Various VPs | Audit Exec | 120 | Campuswide Data - Excluded IT Managed Data | 0 | September through December | Identify protected information/data managed at the department level and confirm adequate security is practiced. | Reduce risk of cyber breach and data ransom including interruption in access to, corruption of, or loss of university data processing systems and/or critical/protected information. Avoid reputation damage.
Post-Tenure Faculty Review Audit | Provost | Audit Exec | 200 | Faculty | 0 | January | Confirm the university's compliance with Florida legislature amended section 1001.706 requiring tenured faculty undergo a comprehensive post-tenure review every five years. | Ensure good standing with State Auditor's office and Board of Governors by complying with Florida laws and regulations.
Follow-up Prior Audit Findings | Various VPs | Audit Exec | 80 | Campus wide | 0 | Depends on Auditee's Remediation Timeline | Evaluate the extent to which reported findings have been remediated. | Improve the control environment to help prevent fraud, improve compliance and assure the achievement of the university's strategic goals.
Performance Funding Metrics | V.P. Finance and Administration | Mauldin & Jenkins Audit Exec | 80 | Remote | 24000 | November through March | Audit to confirm the reliable, complete, accurate and timely reporting of data submissions to the Board of Governors in support the Performance Funding Metrics model. | Assure compliance with Board of Governor's Regulation 5.001, Performance-based Funding, requirement for an annual audit.
Annual DAVID Audit | V.P. Finance and Administration | Audit Exec | 40 | Remote | 0 | July | Audit to confirm the Driver and Vehicle Information Database (DAVID) was only used for authorized activities. | Assure the university has continued access to DAVID for follow-up on parking tickets and to confirm in-state tuition.
Audit of Foundation Dormant Non-endowment Restricted Funds for Management and Disposition in Accordance with Donor Intent | Chief of Staff & Foundation CFO | Audit Exec | 80 | Foundation | 0 | June through January - As Time Permits | Confirm use of restricted funds in in accordance with donor intent per documentation on file. | Funds entrusted to the Foundation to support the university's success sit idle and unused instead of in accordance with the donor's intent.
Pcard Card Charges Continuous Audit | V.P. Finance and Administration | Audit Exec | 80 | Procurement & Accounts Payable | 0 | April, Random | Review executive and other material Pcard user expense report statements for inappropriate expenditures. Confirm controls are operating effectively. Identify any trends in vendor preferences in the past three fiscal years. | The ongoing expenditure review will help mitigate the risk of significant policy violations, adverse public image, and fraud/whistleblower investigation.
Compliance Activities
Work with Compliance Partners on Annual Compliance Reports and Implementation of new laws and regulations. | President's Cabinet | Audit Exec | 80 | Various | 0 | July through September | Work with thirteen university Compliance Partners to prepare annual audit reports, resolve obstacles, and promote compliance. Support General Counsel and leadership team with implementation of new compliance laws and Board of Governor regulations. | Reduce risk of undetected compliance issues.
Develop and implement New and Updated Regulations as University, BOG, State, and Federal requirements change. | V.P. Legal Affairs | Audit Exec | 80 | Remote | 0 | Ongoing | Develop university regulations to mirror new or changed Board of Governor (BOG), state, or Federal regulations and statutes. | Avoid regulatory agency compliance or legal issues. Reduce brand reputation risk from inappropriate conduct.
Annual Review of Consumer Information and other Key Website Information and Links | President's Cabinet | Audit Exec | 24 | Remote | 0 | April | Confirm all compliance information links are functioning, information is current, information is accessible to hearing impaired, and all required sites are listed. | Avoid regulatory agency compliance or legal issues.
Audit University Employee Ongoing Compliance Training Programs | Associate V.P. Human Resources | Audit Exec | 80 | Remote | 0 | July through September | Confirm university's employee training program includes all required Federal, State, and BOG required new employee and refresher training. Confirm all employees participate in training as scheduled. | Avoid legal action, sanctions, and losses associated with compliance violations or inappropriate acts performed by university employees.
Follow-up on NAIA Compliance Reporting | V.P. Legal Affairs | Audit Exec | 40 | Cook Hall | 0 | October | Confirm compliance with NAIA and Title IX regulations. | Personnel do not understand compliance requirements resulting in the violation of laws or regulations, fines, and adverse publicity.
Risk Management
Evaluate Insurance Coverages and Compliance | V.P. Finance and Administration | Audit Exec | 16 | Health & Safety Dept | 0 | December | Support the evaluation of exposures and utilization of insurance coverage as a means of transferring risk. Follow-up on Division of Risk Management report findings. | Losses from operational exposures can be mitigated through the cost effective transfer of risks to insurance pools/coverages.
Maintain COSO Based Enterprise Risk Assessment and Planning (ERM) Model. Add Website and Awareness Training | President's Cabinet | Audit Exec | 120 | Various | 0 | Ongoing | Ongoing risk management meetings with executive management, monitoring changes in key business processes, and tracking economic trends helps facilitates management’s achievement of strategic objectives and minimize the impact of adverse market changes/occurrences. ERM Program implementation continues with creation of a Governance, Risk and Control (GRC) evaluation using the COSO 2017 Integrated Framework. | An enterprise risk management program is required by the Board of Governors for all universities. Program assures significant exposures are cost effectively mitigated and changes in risk are monitored and appropriately responded to.
Follow-up on Succession Planning and Employee Turnover | President's Cabinet | Audit Exec | 24 | All Areas | 0 | July | Minimize the impact of turnover on the achievement of the university's strategic business objectives. | Avoid the loss of institutional knowledge and assure operational continuity to the extent possible.
Management Assists
Support Management on the Strengthening of Internal Control Concerns | President's Cabinet | Audit Exec | 40 | All Areas | 0 | Ongoing | Support management's response and remediation of reported deficiencies from internal and external authorities, as well as management's concerns with new and existing process controls. | Mitigate risks identified by audit activities. Assure timely remediation to avoid repeat findings and promote strong relationships and trust with external audit authorities.
Evaluate Fraud Risk Assessment Ratings | CFO | Audit Exec | 80 | Business and Accounting Areas | 0 | March | Support management's efforts to design and implement effective internal controls to deter fraud, waste and abuse. Continue with Procurement and Budget controls. | Avoid fraud, waste and abuse losses.
Support Management's Development of a Manager/Supervisor Toolkit | Human Resources, Legal Counsel | Audit Exec | 80 | All Areas | 0 | Ongoing | Support management's efforts to improve compliance with university and external regulations by improving manager awareness and preparedness to enforce compliance. | Support management's continuous improvement of compliance with internal and external regulations to reduce the risk of legal actions, accidents, and adverse press.
Develop Facility Key Control Process Narrative | Chief of Staff & AVP Faculties | Audit Exec | 80 | All Areas | 0 | August | Help management understand the controls in place to ensure access to dorms, health faculties, computer rooms, and other sensitive areas is secure. | Help management avoid physical security breaches that could endanger students, private records, executive wellbeing, and access to other valuable university constituents, assets and/or resources.
Support Annual Financial Statement Audit for DSOs | CFO | Audit Exec | 30 | Accounting | 0 | Ongoing | Support management’s development of internal controls over financial reporting to help avoid material errors. | Mitigate risk of financial report error and perception of university's integrity.
Misconduct Investigations
Conduct Misconduct & Compliance Investigations | Various | Audit Exec | 300 | Various | 0 | As Needed | Conduct investigations of alleged misconduct. | Mitigate risk of SUS Board of Governor's or State Legislature's concern with university leadership stewardship of funding and integrity. Avoid public controversy.
Develop Continuous Fraud Detection Tests | Various | Audit Exec | 40 | Various | 0 | As Time Permits | Develop AI agents to continuously monitor accounts payable, payroll, Pcard and other disbursement endpoint activity for potential fraud. | Mitigate risk of SUS Board of Governor's or State Legislature's concern with university leadership stewardship of funding and integrity. Avoid public controversy.
Administration
Develop Audit Committee Agenda Presentations and Minutes | Audit Chairman | Audit Exec | 64 | n/a | 0 | Quarterly | Presentation of Audit, Risk Management, and Compliance efforts to the Audit Committee. | Assures the Audit Committee is well informed of all significant exposures to the achievement of the university's strategic business objectives and compliance with regulatory requirements.
Prepare Annual Internal Audit and Compliance Activities Report | Audit Chairman | Audit Exec | 24 | n/a | 0 | July | Inform the Audit Committee of the Internal Audit and Compliance Department's achievements. | Assure the Internal Audit and Compliance function is effectively operating.
Audit, Risk & Compliance Training | President | Audit Exec | 80 | Various | 8600 | Ongoing | Audit Executive obtain continuing education units to stay aware of current industry issues and maintain certifications. Includes university's internal Skillsoft training. | Develop more effective audit, compliance, and risk management programs.
Update Annual Internal Audit, Risk Management and Compliance Plan | Audit Chairman | Audit Exec | 40 | n/a | 0 | May | Utilize Enterprise Risk Assessment to focus Internal Audit and Compliance resources on highest risks to the achievement of the university's objectives. | Assure optimal coverage of the university's significant exposures.
Optional Work
Support Business Continuity Plan Development | President's Cabinet | Audit Exec | 20 | Various | 0 | Ongoing | Work with management to develop a meaningful plan to minimize the adverse affects of a disaster. Being ill prepared for a disaster can cost lives, affect customer relations, decrease revenues, and/or increase the cost of operations. We believe the investment is essential to the long-term welfare of the employees and achievement of corporate objectives. | Avoid resource losses associated with loss of data, accessibility, operations, financial reporting, etc., due to nature or malicious disaster(s).
Total Hours |  |  | 2262 |  | 52600
Breakdown of Allocation of Hours
Total Internal Audit Hours |  |  | 920 | 40.67%
Total Compliance Hours |  |  | 304 | 13.44%
Total Risk Management Hours |  |  | 160 | 7.073%
Total Investigations Hours |  |  | 340 | 15.03%
Total Management Assist Hours |  |  | 310 | 13.7%
Total Administrative Hours |  |  | 208 | 9.195%
Total Optional Work Hours |  |  | 20 | 0.8842%
Total Hours |  |  | 2262 | 100%
Proposed Internal Audit Budget
Internal Audit Personnel |  | Potential Hours | Planned Hours | Hour Shortfall | Base Pay (Proposed) | Benefits | Budget Per Line Item
Audit Executive |  | 1686 | 2262 | -576 | 186950.4 | 56085.12 | 243035.52
Proposed Co-sourcing | [6 empty] | 44000
Training and Conferences | [6 empty] | 5700
Travel to State University System Events | [6 empty] | 2900
Office Supplies | [6 empty] | 200
Professional Memberships | [6 empty] | 1300
Total Proposed Recurring Budget | [6 empty] | 297135.52
Total proposed Nonrecurring Capital Outlay | [6 empty] | 0
Available Audit Hours Calculation
Hours in Year | 2080
PTO | 274
Administrative* | 120
Total Potential Hours | 1686
* Includes relationship building, continuing education, management meetings, holidays, etc.